## Soil-Net Project Gannt
Soil-Net project Gannt Chart | Updated: 22/6/05
| 2005 | [11 empty] | 2006 | [11 empty] | 2007
| Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26
(1) Project commences | bar: 2005 Jan
Project Coordination meeting | bar: 2005 Feb; 2005 Jun
Project Steering Committee formed | bar: 2005 Feb; 2005 Jul
Web delivery platform confirmed | bar: 2005 Feb; 2005 Jun
Initial topic structure confirmed | bar: 2005 Feb to 2005 Apr
Prototype soil topic selected and written | bar: 2005 Feb; 2005 Jun
Initial linkages with reference schools | bar: 2005 Jul
(1) Provisional soil-texts for teachers made available on Website to access | bar: 2005 May; 2005 Aug
(2) Provisional site-map navigation, structure and architecture presented | bar: 2005 May; 2005 Aug
(1) Provisional developments presented to SETNET and Advisory body of teachers | bar: 2005 Aug; 2005 Oct
(2) Provisional project brand graphic design specifications presented | bar: 2005 Jul
(1) Second test-run of online-materials with educational stakeholders | bar: 2006 Jan; 2006 Apr
(1) Completed Internet product made available and launched | bar: 2006 Apr; 2006 Jul
(1) All supporting documentary material with educational stakeholders | bar: 2006 Nov; 2007 Jan
(1) Project concludes | bar: 2007 Feb
(1) = formal CSG7 Primary Objectives, (2) - Formal CSG7 Secondary Objectives, X = originally stated deadline, R = revised deadlines
Other items are internal project objectives & milestones
Core Work Activity Categories
Educational standards setting
Topic structure development
Soil textual materials authoring - original text
Soil textual materials authoring - student text
Web authoring
Graphic design
Animation development
Schools liaison
Project management
Project Team - Contact details
Steve Hallett: 01525 863255, 0786 7500697, s.hallett@cranfield.ac.uk
Peter Bullock: 01582 768127, peterubullock@aol.com, p.bullock@cranfield.ac.uk
Tom Simmons: 01603 756261, 07803 037897, t.simmons@nsad.ac.uk
Liam Wells: 01603 756261, l.wells@nsad.ac.uk
Jon Dunleavy, 01279 864375, 0791 6282149, jonorono@yahoo.co.uk
Marc Eisenstadt: 01908 65 3149, M.Eisenstadt@open.ac.uk
Carolyn O'Donnell: 01525 408092, Odonnellc@blebp.co.uk
Peter Richardson: 01908 586002, 0772 9103263, peter@ethicalinternet.co.uk